| Pieces | Description | Sub tasks | ETA to be implemented in prod |
| --- | --- | --- | --- |
| Front End | Containerize the Front end and integrate pipelines to update | - Gateway update - Front End Containerization - Github Actions to automate update - Phased approach, starting with Dev > test, QA > test, stag then prod | 2-4 weeks |
| Tasks (data cache, bol verification etc) | Move Python scripts and tasks and containerize them | 8 tasks Convert to Containers or Cron Jobs | 2-4 weeks |
| Function Apps | Move the Function Apps from prod sub to new environments | Determine infrastructure (containers or keep as FA’s) Move Apps | 4 weeks |
| Redis | Move Redis infrastructure from single instance to multiple instances | Determine infrastructure (contained in AKS or individual instances) Move Redis and point resources | 3-5 weeks |
| SQL | Move SQL VM from Prod subscription to new Subscriptions | Create new VM’s or Azure SQL Install SQL Setup DB’s Figure out Security | 6-8 weeks (there is a lot of planning and testing going into this one, trying to find the best way) |
| API’s | Containerize API’s | - Containerize API - Build automation pipeline to update API’s - Address concerns in the code and setup of API’s (memory, plain text security, odd caching behaviors, running django under runserver (which is a lightweight dev server not really meant to run production workloads) | 8-12 weeks (probably the single largest project. We have to build everything out, have deployment in place etc before we can even move on from DEV) |
| Storage | Move away from Azure VM fileshares to individual Fileshares per environment | Migrate data Create fileshares and point everything to it | 2-4 weeks |
| MISC | - | - Create App Config and move our config data into keyvault and app config - Create Front door to direct traffic - Create Infrastructure as Code to build out environment in case it needs to be rebuilt -Finish CI/CD pipelines and work through new deployment model | 2-4 weeks total (individual pieces that get done throughout the project) |

Low end 31 weeks so Mid February

High end 45 weeks so end of May for all of it

(claude has me right in the middle of middle of April)

High end

Project path or phases

Front End

App config

storage

Tasks

API’s

SQL

Redis

Function App